Project Management Plan

Project: Loan Default Prediction

Author: Daria Nikoliouk

Version: 1.0

Date: 27 July 2026

| Version | Date | Author | Change |
| --- | --- | --- | --- |
| 0.1 | Jun 30, 2026 | D. Nikoliouk | Initial project plan — baseline four-phase schedule |
| 1.0 | July 20, 2026 | D. Nikoliouk | Revised to insert a model-iteration phase (Phase 3) after the SQL layer surfaced the missing-DEBTINC finding |

- PURPOSE

This document is the execution plan for the Loan Default Prediction project defined in the Product Requirements Document (PRD). It describes how the work was planned and delivered: the phases, schedule, deliverables, and milestones. It records the mid-project change where a finding in the data layer drove a model iteration. It assumes the problem, scope, and goals set out in the PRD and does not restate them.

- GOALS

| Goal (per PRD §3) | Delivered by | Phase |
| --- | --- | --- |
| Detection — recall ≥70% | Baseline model + validation, then the v2 iteration | Phases 1 & 3 |
| Efficiency — precision + flagged volume | Model comparison and threshold review | Phase 1 |
| Consistency — reproducible scoring with contributing factors | SQL layer + explainability outputs | Phase 2 |

- DELIVERABLES

Technical artifacts

- Python model notebook

- SQL query library (19 queries, five sections)

- Excel control workbook (six tabs, data-quality controls)

- Power BI dashboard (four pages)

- Python model iteration

Project & governance documents

- Product Requirements Document

- MoSCoW prioritization

- Project Plan

- Root README

- Model Risk & Bias Assessment

- SCHEDULE and TIMELINE

| Phase | Planned | Actual | Deliverable | Status |
| --- | --- | --- | --- | --- |
| 1) Data & Model | Week 1 | Week 1 | Cleaned data, baseline model, model comparison, validation | Complete |
| 2) Data Layer & Reporting | Week 2 | Week 2 | SQL library (19 queries), Power BI (4 pages) | Complete |
| 3) Model Iteration | not in baseline | Week 3 | v2 model (missing-DEBTINC flag, recall 69→81) | Complete |
| 4) Documentation & Governance | Week 3-4 | Weeks 4–5 | PRD, MoSCoW, Project Plan, Root README, Bias Assessment | In progress |

- MILESTONES

| Milestone | Phase | When |
| --- | --- | --- |
| Baseline model validated | 1 | End of Week 1 |
| Data layer + dashboard complete | 2 | End of Week 2 |
| Missing-DEBTINC finding confirmed | 2 | Week 2 |
| v2 model complete (recall 69→81) | 3 | End of Week 3 |
| Documentation set complete | 4 | Week 5 (in progress) |

- DEPENDENCIES

The project schedule depended on the fixed sequence of its phases. Because the goal was a working loan-default model, the technical artifacts had to be built in a strict order: the Python model notebook first, then an independent SQL reconciliation of its outputs, then the Power BI dashboard surfacing the key findings. This was a hard chain: the SQL layer had nothing to check until the model produced scores, and the dashboard had nothing to show until the reconciliation confirmed the numbers. Each phase existed to discover or confirm the findings of the one before it.

That sequencing rested on an assumption: that the build would be complete before any model rework was needed. This assumption broke once the hidden missing-DEBTINC finding was confirmed in the SQL layer and connected back to the model — forcing a model iteration the baseline plan didn't contain. Because the project was iterative and solo, the re-plan cost only schedule, not coordination or money: no team to re-align, no budget to renegotiate. Model and fairness risks are addressed in the Model Risk & Bias Assessment.

- SCOPE CHANGE

During the SQL reconciliation in Phase 2, an unexpected pattern surfaced: records where the debt-to-income ratio (DEBTINC) was missing defaulted at roughly 62 percent, about triple the 19.9 percent book-wide rate. DEBTINC was missing on about 21 percent of the book, and its absence was one of the strongest risk signals in the data. The missingness itself was predictive, not noise.

The baseline model handled these gaps with KNN imputation, which fills each missing value with a plausible estimate from similar borrowers. That treatment was reasonable, but it erased the fact that a value had ever been missing, hiding the signal the SQL layer had just uncovered. Rather than remove imputation, the decision was made to keep it and add a new encoded feature, “DEBTINC_missing”, a binary flag capturing which records were originally blank. The flag was engineered before the imputation step, so the information survived, giving the model an independent signal directly aimed at the defaulters v1 had missed. This required retraining the model, which the baseline plan had not included.

The pattern was confirmed in the SQL layer during Week 2, and the resulting model iteration was carried out in Week 3 as an inserted Phase 3. The schedule was revised accordingly: documentation moved from Week 3 to Weeks 4 and 5, and the change was recorded in the version history rather than absorbed silently.

The result justified the cost: the v2 model raised recall from 69 percent to 81 percent, catching defaulters the baseline had missed - a direct gain against the project's primary detection goal.

- APPROACH AND PHASE NOTE

This project was run as four iterative phases rather than Agile sprints. Sprints are a team construct built around fixed cycles and shared ceremonies, as a single-analyst project, therefore a phased and iterative approach has been used in building, analysis, review, and planning, and because the work was iterative, a finding in one phase reshaping a later one was the method working as intended. That is why the Phase 3 model iteration was absorbed as a controlled re-plan rather than a schedule failure.